PT Solar EPC Nusantara

Internal — Enterprise Documentation Standard

BUSINESS PROCESS DOCUMENT

SPMS — Solar Project Monitoring System

Document Code:  SPMS-DOC-03

Document Version:  1.0

Document Status:  Draft

Date:  04 August 2026

Prepared By:  SPMS Documentation Engineering

CONFIDENTIAL — FOR INTERNAL PROJECT USE ONLY

# Revision History

| Version | Date | Author | Description of Changes |
| --- | --- | --- | --- |
| 1.0 | 04 August 2026 | SPMS Documentation Engineering | Initial draft — Business Process Document created for Sprint 1.2, defining the full 8-field process architecture per phase. |

# Document Control

| Document Title | Business Process Document |
| --- | --- |
| Document Code | SPMS-DOC-03 |
| System | SPMS — Solar Project Monitoring System |
| Version | 1.0 |
| Status | Draft |
| Classification | Internal — Enterprise Documentation Standard |
| Prepared By | SPMS Documentation Engineering |
| Reviewed By | Pending Review |
| Approved By | Pending Approval |
| Date | 04 August 2026 |

# Table of Contents

The index below is a live Word field. In Microsoft Word, right-click it and choose "Update Field" (or press F9) to refresh page numbers after editing.

Revision History	i

Document Control	ii

Table of Contents	iii

1. Purpose	1

2. Scope	1

3. Business Objectives	1

4. End-to-End EPC Process	1

Lead	2

Tender	2

Contract Award	2

Notice to Proceed (NTP)	2

Engineering	3

Procurement	3

Construction	3

Mechanical Completion	4

Electrical Completion	4

Testing	4

Commissioning	5

COD (Commercial Operation Date)	5

PAC (Provisional Acceptance Certificate)	5

FAC (Final Acceptance Certificate)	6

Warranty Handover	6

9. Phases Monitored by SPMS	7

10. Handover to PWMS after COD/FAC	7

11. Future Expansion	7

# 1. Purpose

This document defines the end-to-end business process of Solar EPC (Engineering, Procurement, Construction) project execution. It is written from a business analysis perspective and describes how the organization delivers a project as a business, independent of any specific software application or technology.

This document is the Single Source of Truth for the following downstream artifacts, which must remain consistent with the phases, roles, and module mapping defined here:

- Requirement Specification

- Project Blueprint

- Database Design

- Progress Engine

- Dashboard

- Future PWMS Integration

# 2. Scope

This document covers the Solar EPC project lifecycle from initial sales Lead through to Warranty Handover. It applies to all Solar EPC projects delivered by the organization and is intended for use by Business Development, Project Management, Engineering, Procurement, Construction, Commissioning, Quality, and Warranty/Service functions.

# 3. Business Objectives

- Establish one authoritative definition of the Solar EPC business process, phase by phase.

- Define, for every phase, its objective, inputs, activities, outputs, responsible role, progress indicators, and dependencies.

- Establish the mapping between each business process phase and its corresponding SPMS module.

- Define the boundary of responsibility between SPMS and PWMS.

- Provide the single reference used to keep the Requirement Specification, Project Blueprint, Database Design, Progress Engine, and Dashboard consistent with one another.

# 4. End-to-End EPC Process

The Solar EPC business process spans 15 phases, from initial sales Lead through to Warranty Handover. Lead and Tender are summarized briefly, as they are pre-execution commercial activities. Every phase from Contract Award onward is defined using a consistent 8-field structure: Objective, Inputs, Main Activities, Outputs, Responsible Role (PIC), Progress Indicators, Dependencies, and Related SPMS Module.

## Lead

Identification and qualification of a potential Solar EPC opportunity before formal bidding begins. This is a pre-execution, commercial activity and is not tracked in SPMS.

## Tender

Preparation and submission of a technical and commercial proposal in response to a client's tender or RFP. This is a pre-execution, commercial activity and is not tracked in SPMS.

## Contract Award

| Objective | Formalize the EPC contract and establish the legal and commercial basis for project execution. |
| --- | --- |
| Inputs | Awarded tender, negotiated contract terms, client Purchase Order / Letter of Award. |
| Main Activities | Contract negotiation and finalization, legal review, contract signing, internal project registration. |
| Outputs | Signed EPC contract, contract summary, performance bond, internal project code assignment. |
| Responsible Role (PIC) | Contracts Manager / Head of Project Management |
| Progress Indicators | Contract signed (Yes/No); contract effective date recorded. |
| Dependencies | Successful Tender award from client. |
| Related SPMS Module | Project Master |

## Notice to Proceed (NTP)

| Objective | Formally authorize the EPC contractor to begin project execution. |
| --- | --- |
| Inputs | Signed EPC contract, client's NTP letter. |
| Main Activities | Issue/receive NTP letter, project kickoff meeting, mobilization planning, baseline schedule setup. |
| Outputs | NTP record, project kickoff minutes, mobilization plan, baseline schedule. |
| Responsible Role (PIC) | Project Manager |
| Progress Indicators | NTP date recorded; baseline schedule approved. |
| Dependencies | Contract Award completed. |
| Related SPMS Module | Milestone Management |

## Engineering

| Objective | Produce detailed design deliverables sufficient for procurement and construction. |
| --- | --- |
| Inputs | Contract technical specifications, site survey data, client design basis. |
| Main Activities | Detailed design, drawing production, internal/client design review, design approval. |
| Outputs | For-construction drawings, single-line diagrams, engineering calculation packages, bill of quantities. |
| Responsible Role (PIC) | Engineering Manager |
| Progress Indicators | % drawings issued for construction; design approval status. |
| Dependencies | NTP issued; site survey completed. |
| Related SPMS Module | Document Management |

## Procurement

| Objective | Secure and deliver all major equipment and materials required for construction. |
| --- | --- |
| Inputs | Approved engineering drawings, bill of quantities, approved vendor list. |
| Main Activities | Vendor selection, purchase order issuance, expediting, factory acceptance testing, shipment coordination. |
| Outputs | Purchase orders, vendor drawings, FAT reports, delivery schedule, goods receipt records. |
| Responsible Role (PIC) | Procurement Manager |
| Progress Indicators | % purchase orders placed; % equipment delivered to site. |
| Dependencies | Engineering deliverables approved. |
| Related SPMS Module | Material Management |

## Construction

| Objective | Execute all civil, structural, mechanical, and electrical installation works at site. |
| --- | --- |
| Inputs | Approved drawings, delivered materials and equipment, approved construction method statements. |
| Main Activities | Civil works, structural erection, mechanical installation, electrical installation, daily site supervision. |
| Outputs | Daily progress reports, inspection and test records, as-built markups. |
| Responsible Role (PIC) | Site Manager / Construction Supervisor |
| Progress Indicators | % physical progress complete; manpower on site; daily progress logged. |
| Dependencies | Materials delivered; site access and permits secured. |
| Related SPMS Module | Daily Progress |

## Mechanical Completion

| Objective | Confirm all mechanical installation works are complete and ready for electrical works and testing. |
| --- | --- |
| Inputs | Completed mechanical installation, mechanical inspection checklist. |
| Main Activities | Mechanical walkdown, punch list identification, mechanical inspection sign-off. |
| Outputs | Mechanical completion certificate, punch list. |
| Responsible Role (PIC) | QA/QC Engineer |
| Progress Indicators | Mechanical completion certificate issued (Yes/No); punch list item count. |
| Dependencies | Construction (mechanical scope) substantially complete. |
| Related SPMS Module | Inspection |

## Electrical Completion

| Objective | Confirm all electrical installation works are complete and ready for energization testing. |
| --- | --- |
| Inputs | Completed electrical installation, electrical inspection checklist, cable test records. |
| Main Activities | Electrical walkdown, cable/megger testing, punch list identification, electrical inspection sign-off. |
| Outputs | Electrical completion certificate, punch list, cable test reports. |
| Responsible Role (PIC) | Electrical Engineer / QA/QC Engineer |
| Progress Indicators | Electrical completion certificate issued (Yes/No); punch list item count. |
| Dependencies | Construction (electrical scope) substantially complete. |
| Related SPMS Module | Inspection |

## Testing

| Objective | Verify individual systems and components function correctly prior to integrated commissioning. |
| --- | --- |
| Inputs | Mechanical and Electrical Completion certificates, approved test procedures. |
| Main Activities | Pre-commissioning tests, functional tests, non-conformance identification and resolution. |
| Outputs | Test result records, non-conformance reports. |
| Responsible Role (PIC) | Commissioning Engineer |
| Progress Indicators | % test procedures completed and passed. |
| Dependencies | Mechanical and Electrical Completion achieved. |
| Related SPMS Module | Inspection |

## Commissioning

| Objective | Confirm the integrated plant operates as designed prior to energization. |
| --- | --- |
| Inputs | Completed test records, commissioning procedures. |
| Main Activities | Integrated system commissioning, performance verification, commissioning punch list closure. |
| Outputs | Commissioning test reports, commissioning certificate. |
| Responsible Role (PIC) | Commissioning Engineer |
| Progress Indicators | Commissioning certificate issued (Yes/No); open commissioning punch items. |
| Dependencies | Testing phase completed. |
| Related SPMS Module | Milestone Management |

## COD (Commercial Operation Date)

| Objective | Formally declare the plant in commercial operation and generating revenue-grade output. |
| --- | --- |
| Inputs | Commissioning certificate, performance test results. |
| Main Activities | Performance testing, COD declaration, client notification. |
| Outputs | COD certificate, COD notification letter. |
| Responsible Role (PIC) | Project Manager / Head of Project Management |
| Progress Indicators | COD date recorded. |
| Dependencies | Commissioning completed successfully. |
| Related SPMS Module | Milestone Management |

## PAC (Provisional Acceptance Certificate)

| Objective | Obtain the client's provisional acceptance of the completed plant, subject to any outstanding items. |
| --- | --- |
| Inputs | COD certificate, outstanding punch list. |
| Main Activities | Joint inspection with client, punch list agreement, PAC issuance. |
| Outputs | PAC certificate, outstanding punch list, provisional handover documentation. |
| Responsible Role (PIC) | Project Manager |
| Progress Indicators | PAC issued (Yes/No); open punch list items. |
| Dependencies | COD achieved. |
| Related SPMS Module | Document Management |

## FAC (Final Acceptance Certificate)

| Objective | Obtain the client's final acceptance following resolution of outstanding items and the defects liability period. |
| --- | --- |
| Inputs | PAC certificate, closed punch list, completed defects liability period. |
| Main Activities | Final inspection, punch list closure verification, final documentation handover. |
| Outputs | FAC certificate, final documentation package, project close-out report. |
| Responsible Role (PIC) | Project Manager / Head of Project Management |
| Progress Indicators | FAC issued (Yes/No). |
| Dependencies | PAC issued; defects liability period elapsed; punch list closed. |
| Related SPMS Module | Document Management |

## Warranty Handover

| Objective | Transition the plant into its contractual warranty period and hand over ongoing responsibility. |
| --- | --- |
| Inputs | FAC certificate, O&M documentation, warranty terms. |
| Main Activities | Warranty register setup, O&M manual handover, warranty handover meeting. |
| Outputs | Warranty register, O&M manuals, warranty handover certificate. |
| Responsible Role (PIC) | Warranty / Service Manager |
| Progress Indicators | Warranty handover certificate issued (Yes/No). |
| Dependencies | FAC issued. |
| Related SPMS Module | Document Management (handover point to PWMS) |

# 9. Phases Monitored by SPMS

SPMS (Solar Project Monitoring System) is the system of record for Solar EPC project execution. Its monitoring scope begins at Contract Award — when the project is formally registered as a master record — and continues through Final Acceptance Certificate (FAC), covering the full engineering, procurement, construction, testing, commissioning, and acceptance lifecycle.

- Contract Award

- Notice to Proceed (NTP)

- Engineering

- Procurement

- Construction

- Mechanical Completion

- Electrical Completion

- Testing

- Commissioning

- COD (Commercial Operation Date)

- PAC (Provisional Acceptance Certificate)

- FAC (Final Acceptance Certificate)

Lead and Tender precede Contract Award and are pre-execution commercial activities; they are not tracked in SPMS.

# 10. Handover to PWMS after COD/FAC

Once a project reaches Commercial Operation Date (COD) and subsequently achieves Final Acceptance Certificate (FAC), the plant transitions into its contractual warranty period. At this point, SPMS hands over the completed project record — including final documentation, O&M manuals, and warranty terms — to PWMS (Project Warranty Management System), which becomes the system of record for the Warranty Handover phase and all subsequent warranty-period activities, such as claims, expiry tracking, and service visits.

The technical mechanism for this handover (e.g., automated data transfer between SPMS and PWMS) is not yet implemented; it is defined here as a business process requirement and carried forward as a Future Expansion item.

# 11. Future Expansion

- Automated data handover from SPMS to PWMS at FAC (integration or shared data model).

- Progress Engine: automated, weighted progress calculation based on WBS and daily inputs.

- Real-time Dashboard analytics fed directly from phase-level progress indicators.

- Digital PIC assignment and notification workflow per phase.

- Mobile data capture for Construction and Inspection phases.

- Client-facing portal for PAC / FAC sign-off.

- Integration with vendor/factory systems for Procurement tracking.

- A Sales/CRM module to formally capture and track the Lead and Tender phases.