PT Solar EPC Nusantara

Internal — Enterprise Documentation Standard

PROJECT BLUEPRINT

SPMS — Solar Project Monitoring System

Document Code:  SPMS-DOC-05

Document Version:  1.0

Document Status:  Draft

Date:  27 August 2026

Prepared By:  SPMS Documentation Engineering

CONFIDENTIAL — FOR INTERNAL PROJECT USE ONLY

# Revision History

| Version | Date | Author | Description of Changes |
| --- | --- | --- | --- |
| 1.0 | 27 August 2026 | SPMS Documentation Engineering | Initial draft — high-level technical and functional architecture for SPMS (Sprint FT-1), bridging Business Process v1.0, Requirement Specification v1.2, and Progress Engine v1.1 ahead of Database Design. |

# Document Control

| Document Title | Project Blueprint |
| --- | --- |
| Document Code | SPMS-DOC-05 |
| System | SPMS — Solar Project Monitoring System |
| Version | 1.0 |
| Status | Draft |
| Classification | Internal — Enterprise Documentation Standard |
| Prepared By | SPMS Documentation Engineering |
| Reviewed By | Pending Review |
| Approved By | Pending Approval |
| Date | 27 August 2026 |

# Table of Contents

The index below is a live Word field. In Microsoft Word, right-click it and choose “Update Field” (or press F9) to refresh page numbers after editing.

# 5. Purpose and Blueprint Scope

This document defines the high-level technical and functional architecture for SPMS. It is the bridge between the approved business, requirement, and progress-calculation definitions and the detailed database and application design that follow in subsequent sprints.

Business Process

↓

Requirement

↓

Progress Engine

↓

Project Blueprint

↓

Database Design

↓

Application Development

### In Scope

- High-level system architecture, navigation, and module responsibilities.

- Role architecture and access boundaries.

- Architecture principles governing progress, cost, and dashboard behavior.

- Conceptual data flow and report architecture.

### Out of Scope

- Firestore field-level schema and collection design (Database Design sprint).

- Security rules and implementation code (Database Design and Application Development sprints).

# 6. Architecture Principles

| Principle | Description |
| --- | --- |
| Single Source of Truth | Each fact (progress, cost, status) is owned by exactly one component; every other view reads it rather than recomputing or duplicating it. |
| Input Once, Use Everywhere | Field and financial data is captured once at its origin (Daily Progress, Cost Transaction) and reused across Project Master, Dashboard, and Reports without re-entry. |
| Role-Based Access | Every user role has a defined access boundary aligned to its responsibilities (Section 9). |
| No Direct Actual Cost Editing | Actual Cost is always calculated from posted Cost Transactions; no role edits it as an aggregate value. |
| Auditability | Every cost transaction and status change is traceable to its source role and timestamp. |
| Lightweight Database | The data model favors simplicity and maintainability over premature normalization; detailed schema decisions are deferred to the Database Design sprint. |
| Dashboard as Read/Monitoring Layer | The Dashboard renders existing calculated data; it never performs independent business calculation. |
| Future SPMS to PWMS Integration | The architecture anticipates a future handover to PWMS at COD/FAC without requiring rework of SPMS's core data model. |

# 7. High-Level System Architecture

SPMS is organized in four layers. Each layer depends only on the layer below it; no layer bypasses another.

Users

↓

Application Modules

↓

Business Rules / Progress Engine

↓

Data Layer

↓

Dashboard / Reports

| Layer | Responsibility |
| --- | --- |
| Users | The ten roles defined in Section 9, each interacting only with the modules and data their role permits. |
| Application Modules | Dashboard, Project Master, Project Cost Control, and User Management — the four modules defined in Section 8. |
| Business Rules / Progress Engine | Progress calculation, Cost Transaction validation and duplicate detection, and Actual Cost derivation (Sections 12–14). |
| Data Layer | Stores source data and calculated results. Implementation is defined in the Database Design sprint, not here. |
| Dashboard / Reports | Read-only presentation of calculated data; never a source of truth. |

This document does not define database implementation details; those are addressed in the Database Design sprint.

# 8. Navigation Architecture

The final application sidebar has exactly four modules:

| Module | Purpose |
| --- | --- |
| Dashboard | Executive, portfolio-wide monitoring view across all active projects. Read-only. |
| Project Master | A single project's complete operational record: information, team, schedule, progress, documents, issues, and reports. |
| Project Cost Control | Project financial monitoring: Cost Transactions, Actual Cost, and cost-related reporting. |
| User Management | User accounts, roles, and access configuration. |

# 9. User Role Architecture

The following ten roles are the complete set of user roles for this architecture.

| Role | High-Level Responsibility | Access Boundary |
| --- | --- | --- |
| Super Admin | Owns system configuration and platform-wide administration. | Full access to all modules and settings. |
| Head PM | Oversees the project portfolio and approves key milestones and resourcing. | Portfolio-wide read access; approval actions on milestones. |
| Project Manager | Owns delivery of one or more assigned projects. | Full access to assigned projects across all modules. |
| Site Manager | Manages day-to-day site execution and field reporting. | Full access to execution data for assigned site(s). |
| Engineering | Oversees engineering deliverables, drawing status, and technical compliance. | Create/update engineering document status on assigned projects. |
| HSE | Monitors site health, safety, and environmental compliance. | Log HSE observations and inspections on assigned projects. |
| SCM | Coordinates procurement and vendor-related cost inputs. | Create SCM-sourced Cost Transactions on assigned projects. |
| HC | Provides HC-related project expense inputs. | Create HC-sourced Cost Transactions on assigned projects. |
| Finance | Records project and milestone payments. | Create Finance-sourced Cost Transactions on assigned projects. |
| BOD | Approves major investment and strategic direction. | Portfolio-level read access; no transactional access. |

# 10. Dashboard Architecture

| KPI / Panel | Shows |
| --- | --- |
| Total Project | Count of active projects in the portfolio. |
| Overall Progress | Portfolio-wide weighted progress percentage. |
| On Schedule | Count/percentage of projects tracking to plan. |
| On Delay | Count/percentage of projects behind plan. |
| S-Curve | Plan vs. actual progress trend across the portfolio. |
| Engineering Document Status | Aggregate status of engineering deliverables across projects. |
| Procurement Status | Aggregate delivery / purchase-order status across projects. |
| Issue at Site | Open issue counts by severity across active sites. |

### Special Requirements

- No vertical scrolling — all panels fit a single screen.

- Optimized for both desktop and TV display.

- Auto project rotation, default interval 5 minutes.

- Rotation interval is configurable.

- Project filter is configurable.

The Dashboard is a monitoring / read layer. It must not become a separate source of truth or an independent business-calculation engine.

# 11. Project Master Architecture

- Project Master

  - Project List

  - Project Detail

    - Project Information

    - Team Assignment

    - Milestone / Work Structure

    - Overall Progress

    - Weekly S-Curve

    - Activity / Daily Progress

    - Engineering Document Status

    - HSE / Permit Status

    - Site Issues

    - Weekly & Monthly Reports

| Section | High-Level Responsibility |
| --- | --- |
| Project List | Portfolio list of projects with quick filters, entry point to each Project Detail. |
| Project Information | Master data: client, contract, capacity, location, and key dates. |
| Team Assignment | Assigns Project Manager, Site Manager, and other role holders to the project. |
| Milestone / Work Structure | Contractual and internal milestones and the WBS the project is planned against. |
| Overall Progress | Displays the project's calculated overall progress from the Progress Engine (Section 12). |
| Weekly S-Curve | Plan vs. actual progress trend for the project. |
| Activity / Daily Progress | Field-reported daily progress entries feeding the Progress Engine. |
| Engineering Document Status | Status of engineering deliverables for the project. |
| HSE / Permit Status | Safety observations, incidents, and permit status for the project. |
| Site Issues | Open and resolved issues logged for the project. |
| Weekly & Monthly Reports | Generated reports per Section 16, scoped to the project. |

# 12. Progress Engine Architecture

The blueprint preserves the approved progress model: each execution phase contributes progress through its own basis, and these components are aggregated into one overall figure.

| Component | Basis |
| --- | --- |
| Engineering | Document Status + Weight |
| Procurement | Milestone / Weighted Progress |
| Construction | Scope Quantity + Actual Quantity |
| Commissioning | Checklist + Weight |

Progress Components

↓

Project Progress Engine

↓

Overall Progress

↓

Dashboard  ·  S-Curve  ·  Weekly Report  ·  Monthly Report

Component weights are configurable per project. Progress weights must never be hardcoded.

# 13. Project Cost Control Architecture

SCM  ·  HC  ·  Finance

↓

Cost Transaction Ledger

↓

Validation

↓

Duplicate Detection

↓

DRAFT / POSTED / VOID

↓

Actual Cost

↓

Project Cost Control

↓

Dashboard / Reports

Actual Cost is calculated from valid posted transactions and must never be directly editable as an aggregated value.

# 14. Duplicate Prevention Architecture

Only high-level behavior is defined here; detailed Firestore implementation and exact matching algorithms are designed in the next sprint.

| Level | System Behavior |
| --- | --- |
| Exact Duplicate | BLOCK |
| Possible Duplicate | WARNING / REVIEW |

# 15. High-Level Data Flow

User Input

↓

Business Validation

↓

Source Data

↓

Calculation / Aggregation

↓

Read Models

↓

Dashboard / Reports

Dashboard and Reports are not sources of truth.

# 16. Report Architecture

### Weekly Report

- Period Progress

- S-Curve

- Engineering Status

- Procurement Status

- Construction Progress

- Open Issues

- Issues Closed during the reporting period

### Monthly Report

- Monthly Progress Summary

- Monthly S-Curve

- Major Status Summary

- Issue History within the reporting month

- Issue Open Date

- Issue Close Date

# 17. Future SPMS → PWMS Integration

SPMS — Project Execution

↓

COD

↓

Project Completion / Handover Data

↓

PWMS — Warranty Management

- Conceptual flow only — no technical integration, Firebase, or API design at this stage.

- Future integration should avoid unnecessary duplicate data entry between SPMS and PWMS.

# 18. Architecture Decisions and Constraints

- Four main modules only: Dashboard, Project Master, Project Cost Control, User Management.

- Dashboard-first executive monitoring.

- Lightweight document-status monitoring without file uploads.

- Transaction-based Actual Cost.

- Configurable progress weights.

- Role-based access.

- Future integration readiness.

# 19. Future Architecture Expansion

- ERP integration

- Automated data synchronization

- Advanced analytics

- Mobile application

- PWMS integration